## Slide 1
TradieMate
Implementation Plan · 4 Phases · 36 Months
Phase 1
MVP
M1–M8
Phase 2
Traction
M9–M18
Phase 3
Scale
M19–M30
Phase 4
Expand
M31–M36
KEY MILESTONES
M6
Beta launch
10 tradies
M8
50 paying
tradies
M14
Breakeven
350 tradies
M18
500 paying
Seed raise
M24
2,000 tradies
$1M ARR
M30
5,000 tradies
$2.3M ARR
M36
NZ expansion
Series A

## Slide 2
PHASE 1 · MONTH 1–8 · BUILD MVP + SEED 50 TRADIES
Phase 1: Build & Seed
$10–25K investment
Ship MVP
4 core screens: Dashboard · Job Detail · Invoice · Notifications. End-to-end flow working.
50 Beta Tradies
Brisbane plumbers first. Manual onboarding via phone. No credit card required.
First $39 Payment
At least 1 tradie converts to paid plan. Validate willingness to pay before scaling.
Product-Market Fit
3+ invoices/week per tradie. Churn <8%/month. NPS >30 from beta users.
✓ Success = 10 tradies using app daily · 3+ invoices/week each · 1 paying customer · zero data loss

## Slide 3
PHASE 1 · WEEK-BY-WEEK IMPLEMENTATION
8-Week Build Schedule
W1–2
Supabase setup + schema
Auth (Phone OTP)
ABN verify API
React Native + Expo init
W3–4
Dashboard screen
Job Detail screen
Jobs CRUD API
Firebase offline sync
Push notifications FCM
W5–6
Invoice builder UI
GST auto-calc logic
Stripe Tap to Pay
Digital signature pad
W7
Licence upload flow
Doc expiry alerts
Twilio SMS integration
Notification centre
W8
Bug fixes + polish
TestFlight / Play beta
Onboard 5 beta tradies
Manual licence review
Legend:
Core feature
Critical infra
Integration
QA / Launch

## Slide 4
PHASE 1 · TECH DECISIONS + GO-TO-MARKET
Stack Choices & First 50 Tradies
TECH STACK
Mobile
React Native + Expo
iOS + Android · AI-assisted with Cursor
Database
Supabase PostgreSQL
ACID · PgBouncer built-in · Sydney region
Auth
Supabase Phone OTP
Tradies use phone, not email
Realtime
Firebase Firestore
Offline persistence + GPS sync
Payments
Stripe Tap to Pay
1.7% AU cards · no hardware
Hosting
Railway.app
Simple deploys · migrate AWS at 10K users
ACQUIRING FIRST 50 TRADIES
Go to them physically
Visit Bunnings, Reece Plumbing, trade supplier carparks in Brisbane. Meet tradies where they are — not online.
Facebook Groups
Aussie Tradies · Plumbers Network AU. Post problem/solution story — not promo. Engage genuinely.
Free 3-month trial
No credit card. Manual onboarding via 15-min phone call. Goal: get them to create 1 invoice in day 1.
1 suburb, 1 trade
Brisbane plumbers ONLY in M1–3. Density creates word of mouth. Spreading thin = zero momentum.

## Slide 5
PHASE 2 · MONTH 9–18 · TRACTION + BREAKEVEN
Phase 2: Traction
Target: 500 paying tradies · Breakeven
NEW FEATURES
Customer Live Tracking
Uber-style ETA. Tradie taps 'Slide to Start' → customer gets live map link via SMS.
Nearby Supplies Finder
Bunnings, Reece, Tradelink near job site. Google Places API. Supplier sponsorship ready.
Xero Integration
Invoice auto-sync to Xero. BAS-ready. Unlock Xero Marketplace listing.
Verified Badge + Profile
Public tradie profile. Licence verified badge. Customer trust signal.
GO-TO-MARKET
Referral: Refer 1 tradie → 1 free month
Google Ads: intent keywords AU
Master Plumbers AU partnership
TikTok/YouTube: day-in-life content

## Slide 6
PHASE 2 · SPRINT PLAN M9–M18
10-Month Build & Growth Schedule
M9–10
Customer tracking API
Slide to Start UX
Live map customer screen
Twilio SMS ETA alert
M11–12
Xero OAuth integration
Invoice sync to Xero
Xero Marketplace apply
BAS-ready reports
M13–14
Nearby Supplies (Places API)
Supplier filter by trade
Reece/Bunnings pitch
Google Ads launch
M15–16
Public tradie profile
Verified badge system
Reviews & ratings
Referral program live
M17–18
Performance optimisation
PgBouncer add
GPS batch writes
Seed raise prep ($500K ARR)
PHASE 2 KPIs TO TRACK
500
Paying tradies
End M18
$19,500
MRR
End M18
<5%
Monthly churn
Sustained
$50–80
CAC
Avg blended
>60%
Xero users
Of subscribers
>25%
Referral rate
New signups

## Slide 7
PHASE 3 · MONTH 19–30 · SCALE TO 5,000 TRADIES
Phase 3: Scale
Seed raised · Team hired · National
Xero Marketplace launch
Listed as featured app. Accountants recommend TradieMate to tradie clients. CAC ~$0 from this channel.
Earnings Dashboard V2
Per-tradie analytics, tax summaries, BAS export. Reduces churn by giving tradie their own accountant view.
Reece + Bunnings partnership
Supplier sponsorship live. Featured store placement $2–5K/month per region. Revenue stream #2 active.
Infra scale: PgBouncer + Redis
Connection pooler + job queue for Xero async. GPS batching. Handle 2K concurrent users smoothly.
Group/Employer plan
Owner manages 3–5 tradies at $99–149/mo. 3–5x ARPU. Target: 15% of user base on group plan.
PR + case studies
'Jake saved $8K/year using TradieMate'. Target: The Australian, Sky News Trade segment, industry journals.
Target: 5,000 tradies · $2.3M ARR · 15% on Group plan · Supplier sponsorship $60K+/yr

## Slide 8
PHASE 3 · SPRINT PLAN M19–M30
12-Month Scale Schedule
M19–20
Hire: 1 mobile dev
Hire: 1 GTM / sales
Group plan build
Multi-tradie dashboard
M21–22
Xero Marketplace submit
Accountant outreach (50)
Reece sponsorship deal
Featured placement live
M23–24
Earnings Dashboard V2
BAS export / tax summary
PgBouncer + Redis infra
GPS batch optimise
M25–27
Expand: Melbourne + Sydney
Bunnings Power Pass link
PR push — case studies
5-star review campaign
M28–30
Scheduling module V1
Square payment option
Series A prep materials
5,000 tradie milestone
TEAM GROWTH IN PHASE 3
CTO / Tech Lead
Founder
Continues building
CEO / GTM
Founder
Sales + partnerships
Mobile Developer
Hire M19
iOS + Android speed
GTM / Growth
Hire M19
Ads + content + BD
Customer Success
Hire M25
Onboarding + churn

## Slide 9
PHASE 4 · MONTH 31–36 · EXPAND + SERIES A
Phase 4: Expand
NZ · UK · Series A raise
New Zealand launch
NZ market is near-identical — same laws (GST 15%), Xero penetration 70%+, English language. 6-week localisation sprint.
Admin / multi-tradie V2
Business owner view: all crew jobs, earnings, scheduling. Upsell from Solo ($39) to Business ($149+). Target 20% of base.
Series A raise — $2–3M
With 8,000+ tradies, $3M ARR, and 2 markets — Series A is the logical next step. Use for UK expansion and enterprise sales.
UK market exploration
Same language, similar trade compliance (CIS, VAT), high Xero penetration. Start with 1 city pilot (London plumbers).
Enterprise + insurance bundle
Partner with QBE or Allianz for bundled trade insurance. Tradie gets discount through app — sticky, high LTV segment.
In-app parts ordering
Tradie orders parts directly from Reece/Bunnings through app → pickup at store or delivery to job site. 3–8% margin per order.

## Slide 10
FINANCIAL SUMMARY · ALL 4 PHASES · 36 MONTHS
Revenue & Investment by Phase
Chart: Monthly Recurring Revenue Growth
| M6 | M8 | M10 | M12 | M14 | M18 | M20 | M24 | M27 | M30 | M33 | M36
MRR (AUD) | 0 | 390 | 1950 | 7800 | 13650 | 19500 | 35000 | 78000 | 120000 | 195000 | 260000 | 350000
Phase
Invest
Tradies
MRR
Phase 1
$10–25K
50
$1.9K
Phase 2
$250K
500
$19.5K
Phase 3
$500K
5,000
$195K
Phase 4
$2–3M
15K+
$350K+
UNIT ECONOMICS
$780
LTV
$50–80
CAC target
10:1
LTV:CAC
2 months
Payback
Month 14
Breakeven
$2.3M
ARR Year 3
⚠ Key risk: monthly churn >8% pushes breakeven to M18+. Fix: ensure every tradie creates invoice in Day 1 of onboarding.

## Slide 11
RISK REGISTER · ALL PHASES
Risks & Mitigations
Severity
Risk
Impact
Mitigation
HIGH
High churn (>8%/mo)
Breakeven pushed to M18+
Day 1 onboarding: tradie MUST create 1 invoice. Phone call setup. Track weekly.
HIGH
Surcharge ban Oct 2026
Payment flow needs refactor
Build absorb-fee model by default now. Toggle for pass-through. Already planned.
MED
Firebase GPS bottleneck
Location freeze at 500+ concurrent
Batch GPS writes 5s. Socket.io server at 500 tradies. Redis pub/sub buffer.
MED
Xero API rate limiting
Invoice sync failures
BullMQ async job queue from Day 1. Retry with backoff. Never block main request.
MED
ServiceM8 copies features
Lose differentiation
Network effects + supplier partnerships = moat. Speed matters: ship fast.
LOW
Privacy Act compliance
ATO / OAIC penalty
RDS ap-southeast-2. No data leaves AU. Privacy policy from Day 1.

## Slide 12
Immediate Next Steps
This Week
→ Set up Supabase project · Sydney region
→ Init React Native + Expo repo
→ Bolt.new prototype for tradie validation
Month 1
→ Onboard 5 Brisbane plumbers for feedback
→ Build Dashboard + Job Detail screens
→ Stripe test account + webhook setup
Month 2–3
→ Invoice screen + GST logic + Tap to Pay
→ Firebase offline sync
→ 20 beta tradies via Facebook Groups
Month 4–6
→ Formal beta launch → 50 tradies
→ First paying customer conversion
→ Start Xero integration + Reece pitch prep
36 months · 4 phases · $2.3M ARR · 5,000 Australian tradies